## 0. Guidance & Instructions
MANUAL TESTING DOCUMENTATION GUIDE
1. TEST PLAN
Purpose: Defines overall testing approach, scope, timeline, and resources.
Key Components: Project info, scope, testing types, environment, timeline, resources, risks, assumptions.
Who fills it: QA Lead/Test Manager
When: Before testing begins
2. TEST SCENARIOS
Purpose: Describes high-level business situations/workflows to be tested.
Key Components: Scenario ID, name, description, pre-conditions.
Who fills it: QA Lead/Business Analyst
When: During test planning phase
Example: "User Login Scenario" - User provides credentials and system validates them
3. TEST CASES
Purpose: Detailed step-by-step instructions for testing specific functionality.
Key Components: Test case ID, scenario ID, title, pre-conditions, steps, expected result, priority.
Who fills it: QA Engineer/SDET
When: During test design phase
Best Practice: Each test case should be independent and reusable
4. TEST DATA
Purpose: Documents all test data needed for test execution.
Key Components: Data ID, type, test data values, purpose/usage.
Who fills it: QA Engineer/Test Data Manager
When: Before test execution
Important: Use realistic but safe data; never use real production data
5. TEST EXECUTION DOCUMENT
Purpose: Records actual execution results of test cases.
Key Components: Test case ID, cycle, title, executed by, execution date, pass/fail status, defect ID.
Who fills it: QA Engineer
When: During test execution
Status Options: Pass (expected behavior matches actual), Fail (discrepancy found), Not Executed (skipped)
6. TRACEABILITY MATRIX
Purpose: Maps requirements to test cases to ensure complete coverage.
Key Components: Requirement ID, test case ID, requirement description, coverage status.
Who fills it: QA Lead
When: Throughout testing lifecycle
Benefit: Identifies gaps; ensures all requirements are tested
7. DEFECT REPORT
Purpose: Documents all defects/bugs found during testing.
Key Components: Defect ID, test case ID, title, description, severity, priority, status, assigned to.
Who fills it: QA Engineer
When: When defect is discovered
Severity: Critical (blocks functionality), High (major issue), Medium (moderate impact), Low (minor issue)
Priority: Should be set based on business impact
8. TEST SUMMARY REPORT
Purpose: High-level overview of testing results and recommendations.
Key Components: Execution summary, defect summary, metrics, conclusion, recommendation.
Who fills it: QA Lead/Test Manager
When: At end of test cycle
Audience: Stakeholders, Project Manager, Development Lead
KEY METRICS
Pass Rate = (Test Cases Passed / Test Cases Executed) × 100%
Requirement Coverage = (Requirements Tested / Total Requirements) × 100%
Defect Density = Total Defects / Total Test Cases
Escape Rate = Defects found in production / Total defects found (in testing + production)

## 1. Test Plan
TEST PLAN
Project Name:
Test Plan ID: | TP-001
Version: | 1.0
Date: | 06-05-2026
Prepared By:
Approved By:
SCOPE
Features to be Tested:
1.
2.
TESTING TYPE
Functional Testing | ☐
Regression Testing | ☐
Integration Testing | ☐
UAT | ☐
TEST ENVIRONMENT
Environment: | Dev / QA / Staging / Production
Browser/OS:
TIMELINE
Start Date:
End Date:
RESOURCES
QA Lead:
QA Resources:
Test Data Provider:
RISKS & ASSUMPTIONS
Risks:
Assumptions:

## 2. Test Scenarios
Scenario ID | Scenario Name | Description | Pre-conditions
SC-001 | User Login | Valid user login with correct credentials | User account exists
SC-002 | Product Search | Search for product by name | Product catalog loaded
SC-003 | Add to Cart | Add product to shopping cart | Product available in stock

## 3. Test Cases
Test Case ID | Scenario ID | Test Case Title | Pre-conditions | Steps | Expected Result | Priority | Status
TC-001 | SC-001 | Login with valid credentials | Home page loaded | 1. Enter username 2. Enter password 3. Click Login | User redirected to dashboard | High | Not Started
TC-002 | SC-001 | Login with invalid password | Home page loaded | 1. Enter username 2. Enter wrong password 3. Click Login | Error message displayed | High | Not Started
TC-003 | SC-002 | Search by product name | Product page loaded | 1. Click search bar 2. Enter product name 3. Press Enter | Search results displayed | Medium | Not Started

## 4. Test Data
Data ID | Data Type | Test Data | Usage/Purpose
TD-001 | Valid User | Username: testuser@example.com, Password: Test@123 | Valid login scenarios
TD-002 | Invalid User | Username: invalid@example.com, Password: Wrong@123 | Negative test cases
TD-003 | Product Data | Product ID: P001, Name: Laptop, Price: $999 | Product search and purchase
TD-004 | Payment Data | Card: 4532015112830366, CVV: 123 | Payment processing (test card)
TD-005 | Address Data | City: New York, Country: USA, Zip: 10001 | Address validation

## 5. Test Execution
Test Case ID | Cycle | Test Case Title | Executed By | Exec Date | Pass/Fail | Defect ID | Remarks
TC-001 | Cycle-1 | Login with valid credentials | QA-User1 | 15-05-2024 | Pass |  | Executed successfully
TC-002 | Cycle-1 | Login with invalid password | QA-User1 | 15-05-2024 | Fail | DEF-001 | Error message not displayed
TC-003 | Cycle-1 | Search by product name | QA-User2 | 15-05-2024 | Pass |  | Works as expected

## 6. Traceability Matrix
Requirement ID | Test Case ID | Requirement Description | Test Coverage | Status
REQ-001 | TC-001, TC-002 | User should be able to login with valid credentials | Covered | Complete
REQ-002 | TC-003 | User should be able to search products | Covered | Complete
REQ-003 | Not Covered | User should be able to apply discount codes | Not Covered | Pending
REQ-004 | TC-004 | User should be able to checkout | Covered | In Progress

## 7. Defect Report
Defect ID | Test Case ID | Defect Title | Defect Description | Severity | Priority | Status | Assigned To | Found Date | Remarks
DEF-001 | TC-002 | Error message not displayed | When invalid password is entered, error message is not shown to user | High | High | Open | Dev-User1 | 15-05-2024 | Needs investigation
DEF-002 | TC-005 | Typo in button label | Add to Cart button shows "Add To Catrt" | Low | Low | Closed | Dev-User2 | 16-05-2024 | Fixed in build 2.1
DEF-003 | TC-007 | Page loading slowly | Search results page takes 10+ seconds to load | Medium | Medium | In Progress | Dev-User3 | 17-05-2024 | Performance optimization underway

## 8. Test Summary Report
TEST SUMMARY REPORT
PROJECT INFORMATION
Project Name:
Test Cycle: | Cycle-1
Report Date: | 06-05-2026
Prepared By:
EXECUTION SUMMARY
Total Test Cases: | 10
Test Cases Executed: | 8
Test Cases Passed: | 6
Test Cases Failed: | 2
Pass Percentage:
DEFECT SUMMARY
Total Defects: | 3
Critical Defects: | 0
High Defects: | 1
Medium Defects: | 1
Low Defects: | 1
Open Defects: | 1
Closed Defects: | 2
CONCLUSION
Testing Status: | In Progress
Release Readiness: | Pending Defect Resolution
Overall Recommendation: | Not Ready for Production
REMARKS